***** DRAFT not approved by AIP Authority (printed on Thu Feb 12 2026 13:30:44 GMT+1 100 (AEDT)) *****

Australian Jobs Act 2013

AIP Plan reference code: RWT9287F

Australian Industry Participation Plan Summary - Project Phase

Nominated project proponent: WOODERSON SOLAR DEVELOPMENT CO PTY LTD

Project details

Name: Wooderson Solar Farm 
Location: Mount Alma, Queensland 
Type: Electricity facility

Purpose: Establish new facility 
Capital expenditure: $ 1,900,000,000

Description: The project includes a 450-megawatt (MW) solar farm, a 450 MW direct current (DC)-coupled battery energy storage system (BESS) with storage capacity of up to 3,600 megawatt hours (MWh), a 275 kilovolt (kV) overhead transmission line (OHTL), switchyard, and associated ancillary infrastructure. Lead construction contractor procurement will commence in late 2026, with construction anticipated to commence in Q1 2028. Procurement of small works packages is anticipated to commence approximately 6-9 months prior to works commencement.

Completion date: 31 Dec 2030

Page 1 of 5

***** DRAFT not approved by AIP Authority (printed on Thu Feb 12 2026 13:30:44 GMT+1 100 (AEDT)) *****

Key goods and services

Indicative list of key goods and services to be acquired for the project:

| Key goods and services | Opportunities for Australian entities* | Opportunities for non-Australian entities | Explanation for no opportunities for Australian entities |
| --- | --- | --- | --- |

Civil balance of plant	Yes	Yes

Electrical balance of plant	Yes	Yes

Inverters	 No	Yes	There are no qualified Australian suppliers for

utility scale grid-connected projects

Solar panels	No	Yes

Battery cells	No	Yes

Substation equipment	Yes	Yes

Onshore transport	Yes	No

The Proponent has global key supplier

agreements with global suppliers to provide these parts.

The Proponent has global key supplier

agreements with global suppliers to provide these parts.

Construction compound and

operations and maintenance	Yes	No 
facility

High voltage transmission	Yes	No

Commissioning and skilled	Yes	No

labour

Operations and maintenance	Yes	No 
skilled labour

*

An Australian entity is an entity with an ABN or ACN 
Project standards:

Australian 
International

Supplier information and communication

Project proponent’s contact person for supplier enquiries:

Contact person name Lachlan Mitchell

Contact person position Development Project Manager

Phone number 0422139699

E-mail lachlan.mitchell@cqpower.com.au

Project proponent website: https://woodersonsolar.com.au/ 
Project opportunities website:

https://woodersonsolar.com.au/

Supplier engagement and communication actions :

Promote project opportunities through industry associations

Conduct supplier information briefings on project opportunities and bid processes

Issue media releases or ASX announcements on project developments and opportunities

Directly contact suppliers with information on project opportunities and bid processes

Page 2 of 5

***** DRAFT not approved by AIP Authority (printed on Thu Feb 12 2026 13:30:44 GMT+1 100 (AEDT)) *****

Building Australian industry capability

Supplier capability development actions:

Provide market intelligence to suppliers

Encourage Australian entities to undertake research and development and innovative activities

Global supply chain integration actions:

Introduce suppliers to global supply chain partners 
Feedback:

The project proponent will ensure that its procurement entities offer, and if requested, provide feedback to Australian entities whose bids to supply key goods or services for the project have not been successful. Feedback will include recommendations about any relevant training, skills capability and capacity development.

Page 3 of 5

***** DRAFT not approved by AIP Authority (printed on Thu Feb 12 2026 13:30:44 GMT+1 100 (AEDT)) *****

Australian Industry Participation Plan Summary - Operations Phase

Nominated facility operator: WOODERSON SOLAR DEVELOPMENT CO PTY LTD

Facility details

Name: Wooderson Solar Farm 
Location: Mount Alma, Queensland 
Type: Electricity facility

Key goods and services

Indicative list of key goods and services to be acquired for the new facility:

Opportunities for

Australian entities *

Opportunities for 
non-Australian 
entities

Explanation for no opportunities for Australian entities

Key goods and services

Operations and maintenance	Yes	No

skilled labour

High voltage technicians	Yes	No

Other skilled labour and trades	Yes	No

Replacement parts	Yes	Yes

*An Australian entity is an entity with an ABN or ACN 
Facility standards:

Australian 
International

Supplier information and communication

Facility operator’s contact person for supplier enquiries:

Contact person name Lachlan Mitchell

Contact person position Development Project Manager

Phone number 0422139699

E-mail lachlan.mitchell@cqpower.com.au

Facility operator website: https://woodersonsolar.com.au!

Facility opportunities website:

Supplier engagement and communication actions :

Promote project opportunities through industry associations

Conduct supplier information briefings on project opportunities and bid processes

Issue media releases or ASX announcements on project developments and opportunities

Directly contact suppliers with information on project opportunities and bid processes

Page 4 of 5

***** DRAFT not approved by AIP Authority (printed on Thu Feb 12 2026 13:30:44 GMT+1 100 (AEDT)) *****

Building Australian industry capability

Supplier capability development actions:

Provide market intelligence to suppliers

Encourage Australian entities to undertake research and development and innovative activities

Global supply chain integration actions:

Introduce suppliers to global supply chain partners 
Feedback:

The project proponent will ensure that its procurement entities offer, and if requested, provide feedback to Australian entities whose bids to supply key goods or services for the project have not been successful. Feedback will include recommendations about any relevant training, skills capability and capacity development.

Page 5 of 5