***** Approved by AIP Authority on Fri Mar 20 2026 13:21:57 GMT+1100 (AEDT) *****

Australian Jobs Act 2013

AIP Plan reference code: 2V9VKBCH

Australian Industry Participation Plan Summary - Project Phase

Nominated project proponent: CSE H2 Pty Ltd

Project details

Name: Brigalow Peaking Power Plant

Location: 1039 Banana Bridge Rd, Brigalow, QLD

Type: Electricity facility

Purpose: Establish new facility

Capital expenditure: $500 million - $1 billion

Description: The Brigalow Peaking Power Plant is a compact power station with 12 modular turbines capable of using a mix of renewable hydrogen and natural gas. It will supply critical energy to support more renewables entering the power grid in Queensland. The power station will have a capacity of 400 MW, will have fast start capability and is intended to operate in high demand periods to underpin energy security for Queenslanders. Q1 2026 - Q2 2026: Minor works completed on roads around the project Q1 2026 - Q3 2026: Early Works Construction Q3 2026 - Q4 2027: Balance of Plant works Q1 2027 - Q3 2027: GSUT Installation Q4 2026 - Q4 2027: BoP Electrical Works Q4 2027 - Q1 2028: GT Pre-commissioning Q4 2027 - Q4 2028: Hold point testing and approval Q4 2028: COD

Completion date: 01 Jul 2029

Page 1 of 5

***** Approved by AIP Authority on Fri Mar 20 2026 13:21:57 GMT+1100 (AEDT) *****

Key goods and services

Indicative list of key goods and services to be acquired for the project:

| Key goods and services | Opportunities for Australian entities* | Opportunities for non-Australian entities | Explanation for no opportunities for Australian entities |
| --- | --- | --- | --- |

Gas Turbine	Yes	Yes

Gas Turbine Generator	Yes	Yes

Generator Ventilation System	Yes	Yes

Battery System Cells	Yes	Yes

Control Module	Yes	Yes

Turbine Inlet System	Yes	Yes

Turbine Inlet EVAP	Yes	Yes

H2 Blending Skid	Yes	No

Turbine Module	Yes	Yes

Generator Module	Yes	Yes

Piping and Valving	Yes	Yes

Structural Steel	Yes	Yes

Instrumentation	Yes	Yes

Thermal Insulation	Yes	Yes

Cabling	Yes	Yes

Fire System	Yes	Yes

Tanks	Yes	Yes

Earthworks	Yes	No

Road Upgrade	Yes	No

Owners Engineer	Yes	No

Owners Management	Yes	No

HV Connection	Yes	No

Gas Connection	Yes	No

Power Island construction and	Yes	Yes

installation

Water System Upgrade	Yes	No

Auxiliary Buildings	Yes	Yes

Civils	Yes	Yes

*

An Australian entity is an entity with an ABN or ACN 
Project standards:

Page 2 of 5

Australian 
International

***** Approved by AIP Authority on Fri Mar 20 2026 13:21:57 GMT+1100 (AEDT) *****

Supplier information and communication

Project proponent’s contact person for supplier enquiries:

Contact person name Peter Griffiths

Contact person position Future Energy Development Manager

Phone number 0738547777

E-mail cgdevelopment@csenergy.com.au

Project proponent website: https://www.csenergy.com.au/what-we-do/firming-and-storage/brigalow-peaking-power-plant Project opportunities website:

https://www.csenergy.com.au/what-we-do/firming-and-storage/brigalow-peaking-power-plant 
Supplier engagement and communication actions :

Promote project opportunities through industry associations

Conduct supplier information briefings on project opportunities and bid processes

Develop and distribute a supplier information guide for the project

Directly contact suppliers with information on project opportunities and bid processes

Building Australian industry capability

Supplier capability development actions:

Recommend suppliers undertake training and/or accreditation

Support supplier development initiatives of industry associations or governments

Supplier scorecard evaluations and feedback

Global supply chain integration actions:

Provide references for high performing suppliers 
Feedback:

The project proponent will ensure that its procurement entities offer, and if requested, provide feedback to Australian entities whose bids to supply key goods or services for the project have not been successful. Feedback will include recommendations about any relevant training, skills capability and capacity development.

Page 3 of 5

***** Approved by AIP Authority on Fri Mar 20 2026 13:21:57 GMT+1100 (AEDT) *****

Australian Industry Participation Plan Summary - Operations Phase

Nominated facility operator: CSE H2 Pty Ltd

Facility details

Name: Brigalow Peaking Power Plant

Location: 1039 Banana Bridge Rd, Brigalow, QLD

Type: Electricity facility

Key goods and services

Indicative list of key goods and services to be acquired for the new facility:

| Key goods and services | Opportunities for Australian entities | * | Opportunities for non-Australian entities | Explanation for no opportunities for Australian entities |
| --- | --- | --- | --- | --- |

Gas Supply	Yes	No

Electricity Supply	Yes	No

Operators	Yes	No

Plant Management	Yes	No

Water Supply	Yes	No

Hydrogen Supply	Yes	No

Spare Parts	Yes	Yes

Maintenance	Yes	Yes

*An Australian entity is an entity with an ABN or ACN Facility standards:

Australian 
International

Page 4 of 5

***** Approved by AIP Authority on Fri Mar 20 2026 13:21:57 GMT+1100 (AEDT) *****

Supplier information and communication

Facility operator’s contact person for supplier enquiries:

Contact person name Peter Griffiths

Contact person position Future Energy Development Manager

Phone number 0738547777

E-mail csenergytobeinserted@TBC.com

Facility operator website: https://www.csenergy.com.au/what-we-do/firming-and-storage/brigalow-peaking-power-plant Facility opportunities website: https://www.csenergy.com.au/what-we-do/firming-and-storage/brigalow-peaking-power-plant Supplier engagement and communication actions :

Promote project opportunities through industry associations

Conduct supplier information briefings on project opportunities and bid processes

Develop and distribute a supplier information guide for the project

Directly contact suppliers with information on project opportunities and bid processes

Building Australian industry capability

Supplier capability development actions:

Recommend suppliers undertake training and/or accreditation

Support supplier development initiatives of industry associations or governments

Supplier scorecard evaluations and feedback

Global supply chain integration actions:

Provide references for high performing suppliers 
Feedback:

The project proponent will ensure that its procurement entities offer, and if requested, provide feedback to Australian entities whose bids to supply key goods or services for the project have not been successful. Feedback will include recommendations about any relevant training, skills capability and capacity development.

Page 5 of 5