***** DRAFT not approved by AIP Authority (printed on Mon Mar30 2026 14:28:41 GM T+1 100 (AEDT)) *****

Australian Jobs Act 2013

AIP Plan reference code: WA6LAKR9

Australian Industry Participation Plan Summary - Project Phase

Nominated project proponent: GREATLAND PTY LTD

Project details

Name: Havieron Project

Location: Havieron Mine Site, 45km East of Telfer

Type: Mine or quarry

Purpose: Upgrade existing facility

Capital expenditure: $1 billion - $2 billion

Description: The Havieron Project is a brownfield underground goldcopper development in Western Australia that leverages existing infrastructure at the nearby Telfer operation to reduce capital cost, schedule risk and environmental impact. The Project includes development of an underground mine with associated crushing, conveying, ventilation, dewateri ng, paste reticulation, workshops and utilities; surface infrastructure including ROM stockpiles, refrigeration, workshops, administration facilities, accommodation village, evaporation ponds, IT/OT systems and a 33kV power distribution network; a new sealed haul road (-55 km) to transport ore to the Telfer processing facility; a new 132kV transmission line to access latent power capacity at Telfer; and a raw water pipeline to supply Havieron’s longterm water requirements. Havieron is located on the traditional lands of the Martu People. Greatland has an Indigenous Land Use Agreement (ILUA) in place and actively promotes employment, training and procurement opportunities for Martuowned and local Aboriginal businesses. Martu participation requirements are embedded within tender documentation and procurement evaluations. The Project is being delivered under a hybrid EPC and EPCM contracting model. Already engaged parties (FS/early works) will continue providing continuity, and certainty value. EPC arrangements will be applied to defined, selfcontained scopes and major infrastructure packages to provide cost and schedule certainty, while EPCM will be used for integrated and staged works requiring flexibility and close owner involvement. Early works procurement for critical and specialised longlead items commenced following completion of the Feasibility Study in December 2025. Final Investment Decision is targeted for 1 June 2026, with major works commencing postFID. Preproduction activities are planned from June 2026 to September 2028, followed by rampup to steadystate operations.

Completion date: 20 Dec 2028

Page 1 of 3

***** DRAFT not approved by AIP Authority (printed on Mon Mar30 2026 14:28:41 GM T+1 100 (AEDT)) *****

Key goods and services

Indicative list of key goods and services to be acquired for the project:

Key goods and services

Construction and engineering services, detailed design, procurement of goods.

Opportunities for

Australian entities*

Opportunities for 
non-Australian 
entities

Explanation for no opportunities for Australian entities

Yes	No

Long lead procurement items and materials	Yes	No

Supply, installation, engineering, construction,	Yes	No

project controls, procuement

| Underground SM P (structural, mechanical, piping) installation Underground electrical and instrumentation (E&I) installation Ventilation infrastructure installation and commissioning | Yes No Yes No Yes No |
| --- | --- |

Bulk earthworks and site preparation	Yes	No

Haul road and internal road construction	Yes	No

Surface concrete works	Yes	No

Raw water pipeline construction	Yes	No

Highvoltage transmission line construction	Yes	No

(132kV)

Major electrical equipment supply	Yes	No 
(switchgear, transformers, MCCs, VSDs)

Surface electrical and E&I installation	Yes	No

Camp and village facilities (accommodation	Yes	No

and services)

Surface SMP installation	Yes	No

Workshops, maintenance and ancillary	Yes	No

infrastructure

*

An Australian entity is an entity with an ABN or ACN

Project standards:

Australian

International

Page 2 of 3

***** DRAFT not approved by AIP Authority (printed on Mon Mar30 2026 14:28:41 GM T+1 100 (AEDT)) *****

Supplier information and communication

Project proponent’s contact person for supplier enquiries:

Contact person name Procurement Team

Contact person position Manager Commercial

Phone number 0431348942

E-mail HavieronProjectServices@greatland.com.au

Project proponent website: https://www.greatland.com.au/suppliers/

Project opportunities website:

https://www.greatland.com.au/suppliers/

Supplier engagement and communication actions :

Promote project opportunities through industry associations

Engage with vendor identification agencies on project opportunities and bid processes

Conduct supplier information briefings on project opportunities and bid processes

Issue media releases or ASX announcements on project developments and opportunities

Develop and distribute a supplier information guide for the project

Directly contact suppliers with information on project opportunities and bid processes

Building Australian industry capability

Supplier capability development actions:

Recommend suppliers undertake training and/or accreditation

Provide market intelligence to suppliers

Support supplier development initiatives of industry associations or governments

Provide onsite or internal training or accreditation

Encourage Australian entities to undertake research and development and innovative activities

Global supply chain integration actions:

Provide references for high performing suppliers 
Feedback:

The project proponent will ensure that its procurement entities offer, and if requested, provide feedback to Australian entities whose bids to supply key goods or services for the project have not been successful. Feedback will include recommendations about any relevant training, skills capability and capacity development.

Page 3 of 3