***** Draft Not Approved by AIP Authority on Tue Mar 03 2026 1 5:2 1:02 GMT+1 100 (AEDT) *****

Australian Jobs Act 2013

AIP Plan reference code: QFYHYKXW

Australian Industry Participation Plan Summary - Project Phase

Nominated project proponent: GOODMAN PROPERTY SERVICES (AUST) PTY LIMITED

Project details

Name: Project EOS

Location: Sydney, NSW

Type: Other productive facility

Purpose: Establish new facility

Capital expenditure: $500 million or more

Description: The Project is the development of a greenfield data centre, which will involve demolition and bulk excavation, construction, fit out and commissioning of the data centre. The centre comprises electrical systems capable of managing 80MVA of power, the construction of commercial premises to house and operate data servers, including ancillary office space, parking and landscaping. Final investment decision has been reached with construction expected to commence in June 2025. Phase 1 is expected to be complete, commissioned and operational by July 2027, with each of the subsequent phases 2 to 5 completed on a six monthly basis. All phases of the data centre are expected to be complete by July 2029, subject to customer commitment and fitout. Early contractor engagement has commenced with an EPC contractor and the procurement of long-lead items have started. In additional to the EPC contractor, the Project Proponent will be procuring certain key goods and services.

Completion date: 31 Jul 2029

Page 1 of 5

***** Approved 1y AIP Authority on Tue Mar 03 2026 1 5:2 1:02 GMT+1 100 (AEDT) *****

Key goods and services

Indicative list of key goods and services to be acquired for the project:

| Key goods and services | Opportunities for Australian entities* | Opportunities for non-Australian entities | Explanation for no opportunities for Australian entities |
| --- | --- | --- | --- |

LV Diesel Generators	Yes	Yes

UPS Battery Units	Yes	Yes

33kV Distribution	Yes	Yes

Transformers

33kV Switchboards	Yes	Yes

Ring Main Units	Yes	Yes

Water Cooled Chillers	Yes	Yes

Fan Wall Units	Yes	Yes

Civil Works	Yes	No

Piling	Yes	No

Formwork	Yes	No

Reinforcement Supply & Fix	Yes	No

Concrete (including Post-	Yes	No

Tensioning)

Precast	Yes	Yes

Blockwork	Yes	No

Structural Steel	Yes	Yes

Metalwork	Yes	Yes

Roofing	Yes	No

Waterproof Membrane	Yes	No

Facade/Louvres	Yes	Yes

Internal Floor Finishes	Yes	No

Epoxy Flooring	Yes	No

Partitions and Drywall	Yes	No

Doors & Frames	Yes	No

Structural Ceilings	Yes	Yes

Painting	Yes	No

Tower / Mobile Cranes	Yes	No

Scaffold & Access	Yes	No

Furnishing & Joinery	Yes	Yes

Technical Cleaning	Yes	No

Traffic Control	Yes	No

Electrical Services	Yes	No

Mechanical Services	Yes	No

Dry & Wet Fire Services	Yes	No

Hydraulic Services	Yes	No

BMS / DCS Controls	Yes	Yes

ICT Services	Yes	Yes

Security Services	Yes	Yes

Lifts	Yes	Yes

Site Establishment /	Yes	No

Temporaries

*

An Australian entity is an entity with an ABN or ACN 
Project standards:

Page 2 of 5

Australian 
International

***** Approved 1y AIP Authority on Tue Mar 03 2026 1 5:2 1:02 GMT+1 100 (AEDT) *****

Supplier information and communication

Project proponent’s contact person for supplier enquiries:

Contact person name Brendon Quinn

Contact person position General Manager

Phone number 0292307402

E-mail Brendon.Quinn@goodman.com

Project proponent website: https://au.goodman.com/property-lease-site/2-8-lanceley-place 
Project opportunities website:

https://au.goodman.com/property-lease-site/2-8-lanceley-place 
Supplier engagement and communication actions :

Promote project opportunities through industry associations

Conduct supplier information briefings on project opportunities and bid processes

Develop and distribute a supplier information guide for the project

Directly contact suppliers with information on project opportunities and bid processes

Regular attendance and provision of project information at industry conferences

Building Australian industry capability

Supplier capability development actions:

Recommend suppliers undertake training and/or accreditation

Encourage Australian entities to undertake research and development and innovative activities

Provide feedback on supply chain capabilities to encourage timeliness in line with industry standards

Global supply chain integration actions:

Provide references for high performing suppliers 
Feedback:

The project proponent will ensure that its procurement entities offer, and if requested, provide feedback to Australian entities whose bids to supply key goods or services for the project have not been successful. Feedback will include recommendations about any relevant training, skills capability and capacity development.

Page 3 of 5

***** Approved 1y AIP Authority on Tue Mar 03 2026 1 5:2 1:02 GMT+1 100 (AEDT) *****

Australian Industry Participation Plan Summary - Operations Phase

Nominated facility operator: GOODMAN PROPERTY SERVICES (AUST) PTY LIMITED

Facility details

Name: Project EOS

Location: Sydney, NSW

Type: Other productive facility

Key goods and services

Indicative list of key goods and services to be acquired for the new facility:

| Key goods and services | Opportunities for Australian entities | * | Opportunities for non-Australian entities | Explanation for no opportunities for Australian entities |
| --- | --- | --- | --- | --- |

Security Guards	Yes	No

Cleaning	Yes	No

Electricity Supply	Yes	No

Fuel Supply	Yes	No

Water Supply	Yes	No

Maintenance & Services	Yes	No

Contracts

Technical Staff! Management	Yes	No

Telecommunication Services	Yes	No

*An Australian entity is an entity with an ABN or ACN 
Facility standards:

Australian 
International

Page 4 of 5

***** Approved 1y AIP Authority on Tue Mar 03 2026 1 5:2 1:02 GMT+1 100 (AEDT) *****

Supplier information and communication

Facility operator’s contact person for supplier enquiries:

Contact person name Brendon Quinn

Contact person position General Manager, Data Centre Delivery

Phone number 0292307402

E-mail Brendon.Quinn@goodman.com

Facility operator website: https://au.goodman.com/property-lease-site/2-8-lanceley-place

Facility opportunities website: The following website is a landing page for the site and will be updated once known: https://au.goodman.com/property-lease-site/2-8-lanceley-place

Supplier engagement and communication actions :

Promote project opportunities through industry associations

Conduct supplier information briefings on project opportunities and bid processes

Develop and distribute a supplier information guide for the project

Directly contact suppliers with information on project opportunities and bid processes

Regular attendance and provision of facility information at industry conferences

Building Australian industry capability

Supplier capability development actions:

Recommend suppliers undertake training and/or accreditation

Encourage Australian entities to undertake research and development and innovative activities

Provide feedback on supply chain capabilities to encourage timeliness in line with industry standards

Global supply chain integration actions:

Provide references for high performing suppliers 
Feedback:

The project proponent will ensure that its procurement entities offer, and if requested, provide feedback to Australian entities whose bids to supply key goods or services for the project have not been successful. Feedback will include recommendations about any relevant training, skills capability and capacity development.

Page 5 of 5