***** DRAFT not approved by AIP Authority (printed on Wed Apr 15 2026 1 5:00:10 GMT+1000 (AEST)) *****

Australian Jobs Act 2013

AIP Plan reference code: X5J7VX5M

Australian Industry Participation Plan Summary - Project Phase

Nominated project proponent: PILGANGOORA OPERATIONS PTY LTD

Project details

Name: P2000 Expansion Project

Location: Pilgangoora Mine Site, Marble Bar, Western Australia 6760

Type: Other productive facility

Purpose: Upgrade existing facility

Capital expenditure: $500 million or more

Description: The Project aims to duplicate the existing Pilgangoora operation and increase total throughput from 1Mtpa to produce 1.85Mtpa of high quality lithium products. This expansion will be delivered through the design and construction of new processing facilities integrated with the current operation. The scope of works includes, but is not limited to, the development of the following major infrastructure components: Dry Plant - Primary Crushing Hub, Oversize Screening and Conveying, Screen House and Conveying, Ore Sorting Building and Conveying, Coarse Ore Stockpile and Stacker, Coarse Ore Reclaimer and Pebble Crushing, Eject Stock Piling and Conveying Wet Plant - Classification and Milling, Magnetic Separation, Pre-floatation recovery, Floatation Recovery, concentrate de-watering and stockpiling, Tailings Thickening and Disposal, Tantalum Processing and stockpiling, Tailings Filtration and Dry Stacking Process Plant Utilities - Process Water Dams, Air Services, Water Services, Reagents, Power Reticulation. Construction Packages - Key construction packages for the Project will include - Demolition, Bulk Earthworks, Detailed Earthworks and Concrete, Steel Fabrication, Structural, Mechanical, Piping and Electrical and Instrumentation Installation, Commissioning. A level 3 Project estimate is currently being developed to facilitate a Financial Investment Decision by the PLS Board in September 2026. High Level Timeline: Pre-FID decision for facilitate procurement of long lead items - May 2026 Procurement of long lead items - May 2026 Full Project FID - September 2026 Procurement of Remaining supply contracts commencing - September 2026 Construction commencement - November 2026 Project Completion - March 2029 This Project will be self-funded by the business.

Completion date: 31 Mar2029

Key goods and services

Indicative list of key goods and services to be acquired for the project:

| Key goods and services | Opportunities for Australian entities* | Opportunities for non-Australian entities | Explanation for no opportunities for Australian entities |
| --- | --- | --- | --- |

Detailed Engineering - Dry Plant	Yes	No

Detailed Engineering - Wet Plant	Yes	No

Geotech	Yes	No

Surveying	Yes	No

Control System Integrator	Yes	No

Page 1 of 3

***** DRAFT not approved by AIP Authority (printed on Wed Apr 15 2026 1 5:00:10 GMT+1000 (AEST)) *****

Structural Steel, Platework and	Yes	Yes

Piping Fabrication

Demolition and Rehabilitation	Yes	No

Bulk Earthworks	Yes	No

Concrete and Detailed Earthworks -	Yes	No

Dry Plant

Concrete and Detailed Earthworks -	Yes	No 
Wet Plant

SMP/E&I - Dry Plant	Yes	No

SMP/E&I - Wet Plant	Yes	No

Ball Mill	Yes	No

Thickeners	Yes	No

Flotation Cells	Yes	No

Onstream Analyser	Yes	No

Belt Filter	Yes	No

WHIMS	Yes	No

Sag Mill	Yes	No

Primary Crusher	Yes	No

Cone Crusher	Yes	No

Apron Feeders	Yes	No

Ore Sorters	Yes	No

Screens	Yes	Yes

Vibrating Pan Feeders	Yes	Yes

Slurry Pumps	Yes	Yes

Cyclones	Yes	No

Agitators	Yes	No

Actuated & Manual Valves	Yes	No

Special Piping Items	Yes	No

Chiller Plant	Yes	No

Cranes & Hoists	Yes	No

Compressors, Blowers, Dryers and	Yes	No

Receivers

Pebble Crusher	Yes	No

Conveyor Belt	Yes	No

Conveyor Pulleys	Yes	No

Conveyor Idlers	Yes	Yes

Conveyor Drives	Yes	Yes

Conveyor Skirts	Yes	No

Lubricators	Yes	No

Belt Feeders	Yes	No

HV VSD	Yes	No

Transformers	Yes	No

LV & HV Transportable Switchrooms	Yes	No

HV Switchgear	Yes	No

LV VSDs	Yes	No

Controle System Hardwear	Yes	No

Misc Electrical Panels	Yes	No

Cables	Yes	No

Lights and Light Poles	Yes	No

Flow Instruments	Yes	No

Plant Buildings	Yes	No

COS Dome	Yes	Yes

Structural Steel, Platework and	Yes	Yes

Piping Fabrication

Page 2 of 3

*An Australian entity is an entity with an ABN or ACN

***** DRAFT not approved by AIP Authority (printed on Wed Apr 15 2026 1 5:00:10 GMT+1000 (AEST)) *****

Project standards:

Australian

Supplier information and communication

Project proponent’s contact person for supplier enquiries:

Contact person name Michael Lenihan

Contact person position Contract Manager- Major Projects

Phone number 0450404131

E-mail Michael.Lenihan@PLS.com

Project proponent website: https://gateway.icn.org.au/projects/18385?view_type=test 
Project opportunities website:

https://gateway.icn.org.au/projects/18385?view_type=test 
Supplier engagement and communication actions :

Promote project opportunities through industry associations

Conduct supplier information briefings on project opportunities and bid processes

Issue media releases or ASX announcements on project developments and opportunities

Directly contact suppliers with information on project opportunities and bid processes

Building Australian industry capability

Supplier capability development actions:

Encourage joint ventures and alliances between suppliers

Support supplier development initiatives of industry associations or governments

Global supply chain integration actions:

Provide references for high performing suppliers 
Feedback:

The project proponent will ensure that its procurement entities offer, and if requested, provide feedback to Australian entities whose bids to supply key goods or services for the project have not been successful. Feedback will include recommendations about any relevant training, skills capability and capacity development.

Page 3 of 3