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Australian Industry Participation Plan Summary – Project Phase
Nominated project proponent:
QUEENSLAND ELECTRICITY TRANSMISSION CORPORATION LIMITED

Project details
Project name:
Bungaban Wind Farm Connection Project
Location:
Bungaban
Type:
Electricity facility
Purpose:
Establish new facility
Capital expenditure:


Capital expenditure:
 Confirm the total project estimated capital expenditure value will be $500 million or more

Description:
The Bungaban Wind Farm Connection Project relates to the connection of the proposed 1.4GW Bungaban Wind Farm, located approximately 40km north-east of Wandoan in Queensland, to Powerlink's existing transmission network via the Wandoan South Substation. The project involves construction of a new substation at the wind farm site and a double circuit 275kV transmission line between the wind farm and the existing substation, together with the associated and supporting infrastructure such as towers, conductors and access tracks. The project is currently in planning and approvals, including environmental assessment under the Environment Protection and Biodiversity Conservation Act 1000, with controlled action determination made in February 2026 and preliminary documentation to be prepared and release for public comment. Procurement is being undertaken through a two-stage interactive tender process, comprising a non-binding Stage 1 followed by a binding Stage 2, where proponents submit progressively detailed proposals and negotiation prior to contract award. The process includes evaluation and approvals prior to contract execution, with a design and construct deliver contract to be finalised. The current program indicates tendering activities occurring through 2026, with contractor selection, approvals and contract execution targeted in early 2027, followed by notice to proceed and commencement of early civil design and early works during 2027, and progression into delivery under the design and construction contract thereafter. The total estimated capital expenditure for the Bungaban Wind Farm Connection Project is expected to exceed $500 million. There is currently no confirmed Australian Government funding, grant or direct investment identified for the project.
Estimated completion date:
1/09/2029
Key goods and services
Indicative list of key goods and services to be acquired for the project:
List of key goods and services:
An Australian entity is an entity with an ABN or CAN.

	Key goods and services	Opportunity for entities
	Explanation for no opportunities for Australian entities

	Buying land rights for the line - Valuers, land agents and lawyers to secure the easement with landholders
	Opportunities for Australian entities	

	Land surveying - Surveying and registering the easement and substation land
	Opportunities for Australian entities	

	Environmental approvals - Ecology surveys and development of materials required for environmental approvals
	Opportunities for Australian entities	

	Cultural heritage assessments and related Traditional Owner engagement
	Opportunities for Australian entities	

	Ground testing - Drilling boreholes to test ground conditions
	Opportunities for Australian entities	

	Contamination testing
	Opportunities for Australian entities	

	Substation high-voltage equipment
	Opportunities for Australian entities	

	Tower steel
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Wires and insulators - Power line wire, fibre optic earth wire, insulators and fittings
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Freight
	Opportunities for Australian entities	

	Customs clearance support
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Switching on the new assets
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Access tracks
	Opportunities for Australian entities	

	Access Track Maintenance
	Opportunities for Australian entities	

	Gravel and road base
	Opportunities for Australian entities	

	Gates, grids and fencing
	Opportunities for Australian entities	

	Vegetation clearing
	Opportunities for Australian entities	

	Earthworks
	Opportunities for Australian entities	

	Tower foundations
	Opportunities for Australian entities	

	Concrete
	Opportunities for Australian entities	

	Reinforcing steel
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Tower building
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Stringing the wires
	Opportunities for Australian entities	

	Crossing protection
	Opportunities for Australian entities	

	Tower earthing
	Opportunities for Australian entities	

	Substation civil works
	Opportunities for Australian entities	

	Substation steel structures
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Substation buildings
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Electrical installation
	Opportunities for Australian entities	

	Control and protection panels
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Backup power systems - Standby generator, batteries and power boards
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Communications - Fibre optic cabling and communications equipment
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Security systems - Access control and building security
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Signs and Signage
	Opportunities for Australian entities	

	Scaffolding
	Opportunities for Australian entities	

	Engineering design
	Opportunities for Australian entities	

	Construction surveying
	Opportunities for Australian entities	

	Materials testing
	Opportunities for Australian entities	

	Workforce accommodation
	Opportunities for Australian entities	

	Site setup - Site offices, toilets and laydown yards
	Opportunities for Australian entities	

	Cranes
	Opportunities for Australian entities	

	Plant and vehicle hire
	Opportunities for Australian entities	

	Local transport
	Opportunities for Australian entities	

	Fuel - Diesel supply and delivery
	Opportunities for Australian entities	

	Water supply and carting for construction and dust control
	Opportunities for Australian entities	

	Biosecurity and washdowns
	Opportunities for Australian entities	

	Environmental management
	Opportunities for Australian entities	

	Traffic control
	Opportunities for Australian entities	

	Waste - Rubbish removal and recycling
	Opportunities for Australian entities	

	Security guards - Securing yards and stored materials and security fencing and devices
	Opportunities for Australian entities	

	Labour hire and trades
	Opportunities for Australian entities	

	Training - Inductions, 4WD and safety training
	Opportunities for Australian entities	

	Bus transport - Buses between accommodation and site
	Opportunities for Australian entities	

	Drones and helicopters - Aerial support for stringing, inspection and survey
	Opportunities for Australian entities	

	PPE, uniforms, signs and office supplies
	Opportunities for Australian entities	



Project standards:
Australian, International


Supplier information and communication
Project Proponents Contact Person
Project proponent’s contact person for supplier enquires.
Contact person’s name:
Sam Scandlyn
Contact person’s position:
Local Economic Participation Specialist
Phone number:
0738984439
Email address:
sam.scandlyn@powerlink.com.au

Project Proponent Website
Project proponent website:
https://www.powerlink.com.au/projects/bungaban-wind-farm-connection-project

Project Opportunities Website
List of websites:
	Is this website active?	Is this website active?
	Date the website is expected to go live:

	https://www.powerlink.com.au/projects/bungaban-wind-farm-connection-project
	Yes	


Supplier engagement and communication actions:
Promote project opportunities through industry associations
Develop and distribute a supplier information guide for the project




Building Australian industry capability
Supplier capability development actions:
Recommend suppliers undertake training and/or accreditation
Support supplier development initiatives of industry associations or governments

Global supply chain integration actions:
Introduce suppliers to global supply chain partners

Feedback:
Confirm you, and/or your procurement entities will offer and, if requested,  provide feedback to unsuccessful Australian entities whose bids to supply key goods or services for the project have not been successful
Confirm feedback provided to unsuccessful bidders will include any recommendations of relevant training, skills, capability and capacity development
Confirm you will collect written evidence of feedback offered or provided to unsuccessful bidders





Australian Industry Participation Plan Summary – Operations Phase
Nominated facility operator:
QUEENSLAND ELECTRICITY TRANSMISSION CORPORATION LIMITED
Facility details
Facility name:
Bungaban Wind Farm Connection Project
Location:
Bungaban
Type:
Electricity facility
Key goods and services
Indicative list of key goods and services to be acquired for the new facility:
List of key goods and services:
An Australian entity is an entity with an ABN or CAN.

	Key goods and services	Opportunity for entities
	Explanation for no opportunities for Australian entities

	Land surveying
	Opportunities for Australian entities	

	Freight
	Opportunities for Australian entities	

	Switching on the new assets
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Access tracks
	Opportunities for Australian entities	

	Gravel and road base
	Opportunities for Australian entities	

	Gates, grids and fencing
	Opportunities for Australian entities	

	Vegetation clearing
	Opportunities for Australian entities	

	Earthworks
	Opportunities for Australian entities	

	Tower foundations
	Opportunities for Australian entities	

	Concrete
	Opportunities for Australian entities	

	Reinforcing steel
	Opportunities for Australian entities	

	Tower building
	Opportunities for Australian entities	

	Stringing the wires
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Crossing protection
	Opportunities for Australian entities	

	Tower earthing
	Opportunities for Australian entities	

	Substation civil works
	Opportunities for Australian entities	

	Substation buildings
	Opportunities for Australian entities	

	Electrical installation
	Opportunities for Australian entities	

	Control and protection panels
	Opportunities for Australian entities	

	Backup power systems
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Communications - Fibre optic cabling and communications equipment
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Security systems - Access control and building security
	Opportunities for Australian entitiesOpportunities for non-Australian entities	

	Signs and Signage
	Opportunities for Australian entities	

	Scaffolding
	Opportunities for Australian entities	

	Engineering design
	Opportunities for Australian entities	

	Construction surveying
	Opportunities for Australian entities	

	Materials testing
	Opportunities for Australian entities	

	Workforce accommodation
	Opportunities for Australian entities	

	Site setup - Site offices, toilets and laydown yards
	Opportunities for Australian entities	

	Cranes
	Opportunities for Australian entities	

	Plant and vehicle hire
	Opportunities for Australian entities	

	Local transport
	Opportunities for Australian entities	

	Fuel - Diesel supply and delivery
	Opportunities for Australian entities	

	Water supply and carting for construction and dust control
	Opportunities for Australian entities	

	Biosecurity and washdowns
	Opportunities for Australian entities	

	Environmental management
	Opportunities for Australian entities	

	Traffic management at road crossings
	Opportunities for Australian entities	

	Waste - Rubbish removal and recycling
	Opportunities for Australian entities	

	Security services
	Opportunities for Australian entities	

	Labour hire and trades
	Opportunities for Australian entities	

	Training - Inductions, 4WD and safety training
	Opportunities for Australian entities	

	Bus transport
	Opportunities for Australian entities	

	Drones and helicopters
	Opportunities for Australian entities	

	PPE, uniforms, signs and office supplies
	Opportunities for Australian entities	



Facility standards:
Australian, International


Supplier information and communication
Facility operators Contact Person
Facility operators contact person for supplier enquires.
Contact person’s name:
David Wigginton
Contact person’s position:
Development Director
Phone number:
0428833121
Email address:
david.wigginton@powerlink.com.au

Facility Operator Website
Facility operator website:
https://www.powerlink.com.au/projects/bungaban-wind-farm-connection-project

Facility Opportunities Website
List of websites:

	Website address (URL only)	Is this website active?
	Date the website is expected to go live:

	https://www.powerlink.com.au/projects/bungaban-wind-farm-connection-project
	Yes	


Supplier engagement and communication actions:
Promote new facility opportunities through industry associations
Conduct supplier information briefings on new facility opportunities and bid processes




Building Australian industry capability
Supplier capability development actions:
Recommend suppliers undertake training and/or accreditation
Support supplier development initiatives of industry associations or governments

Global supply chain integration actions:
Introduce suppliers to global supply chain partners

Feedback:
Confirm feedback provided to unsuccessful bidders will include any recommendations of relevant training, skills, capability and capacity development
Confirm you will collect written evidence of feedback offered or provided to unsuccessful bidders
Confirm you, and/or your procurement entities will offer and, if requested,  provide feedback to unsuccessful Australian entities whose bids to supply key goods or services for the new facility have not been successful
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